## Sheet1
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress | Project_Days_Summary
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78% | Project Name | Total Days Required
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100% | Consulting | 92
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45% | Customer Svc | 77
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% | Development | 100
Product Dev | Prototype Development | Ethan | 2024-02-01 | 18 | 2024-01-20 | 100% | Engineering | 74
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% | Events | 80
Product Dev | User Interface Design | Gabriel | 2024-04-02 | 25 | 2024-02-29 | 0% | Financial | 68
Customer Svc | Service Improvement | Hannah | 2024-01-02 | 22 | 2024-02-23 | 100% | Logistics | 75
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100% | Marketing | 74
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% | Operations | 75
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | Product Dev | 53
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-09-02 | 78% | Production | 96
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100% | Research | 82
Research | Market Trends Analysis | Nathan | 2024-02-01 | 23 | 2024-01-25 | 50% | Sales | 115
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0% | Support | 78
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0% | Training | 79
Development | Software Development | Quinn | 2024-02-01 | 36 | 2024-07-02 | 100%
Development | Feature Enhancement | Rachel | 2024-08-02 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-03-01 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-05-04 | 0%
Sales | Lead Generation | Wendy | 2024-03-01 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-06-01 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-03-02 | 35 | 2024-09-03 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-02-03 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-03-01 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-03-02 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-02-01 | 35 | 2024-06-02 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-05-03 | 0%
Consulting | Client Advisory | Helen | 2024-06-03 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-04-01 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-03-01 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-03-02 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-03-01 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-02-01 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%